## Sheet3
Test case for Probashi App
|  | TC Start Date | 2023-11-07 | TC Execution Start Date | 2023-11-07 | TEST CASE SUMMARY
|  | TC End Date | 2023-11-07 | TC Execution End Date | 2023-11-07 | PASS | 5
|  | Test Case Developed By | Md Ahsan Habib | Device | VIVO | FAIL | 2
|  | Test Case Reviewed By |  | Operating System | FuntouchOS | WARNING | 0
|  | Test Executed by | Md Ahsan Habib | Version | 1.1.12
Test Case ID | TC Title | Test Case Description | Test Data | Step Description | Expected Result | Actual Result | Status | Remarks | Testing Type | Priority
TC# 001 | Launching The APP | To verify whether the application (Probashi App) behaves as expected whenever it starts/stops. | 1. Probashi App. 2. Internet Connection. | 1. Download the app from the google play store. 2. Install on Vivo Y19 3. Run the app 4. Close the app | App Should open and close smoothly. | App is open and closing as expected | Passed |  | Functional
TC# 002 | App Language's | To validate whether the application's language is working or not. | 1. Probashi App. 2. Internet Connection. | 1. Open the app. 2. Tap on Engish 3. Tap on Bangla | When the user selects Bengali as the language everything should be shown in Bangla, Also for English | Here, the language of the app interface just changes but "Terms and Conditions" and many more were not changed | Failed | https://drive.google.com/file/d/1pyh5l2du2rROFETxArmUivQIjsEe3Bg-/view?usp=sharing | Functional | High
TC# 003 | Registration Process | Register with a valid information. | 1. Probashi App. 2. Internet Connection. | 1. Launch the "Probashi App.". 2. Click on the "Sign Up. 3. Enter valid user details (name, email, password, etc.) 4. Submit the registration form. | Successful registration and creation of a new user account. | The registration process was successful. A new user account was created, and the user was redirected to the login screen. | Passed |  | Functional
TC# 004 | Login Process | User Login with an valid cridentials | 1. Probashi App. 2. Internet Connection. | 1. Launch the "Probashi App.". 2. Enter the registered email and password. 3. Click on the "Sign in" button | Successful login, granting access to the user's account dashboard. | The login process was successful. The user was granted access to the account dashboard, where their information and relevant features were displayed correctly. | Passed |  | Functional
TC# 005 | Invalid Login Attempt | Trying to log in with invalide cridentials | 1. Probashi App. 2. Internet Connection. | 1. Launch the "Probashi App.". 2. Enter an invalid email or password combination. 3. Click on the "Sign in" button | Display of an appropriate error message indicating invalid credentials. | The app is displayed a proper error message to the user. It's showing DioError, which will not be understandable to users | Failed | https://drive.google.com/file/d/1qARDG-vYnV4O3a8yLkjbGM6rA5-EmHdD/view?usp=sharing | Functional | High
TC# 006 | Password Reset | To verify whether the Password Reset function of the application works as expected. | 1. Probashi App. 2. Internet Connection. | 1. Launch the "Probashi App.". 2. Click on the "Forgot Password" link. 3. Enter the registered email address. 4. Submit the password reset request. | Successful password reset email sent to the registered email address. | The password reset process was successful. The user received a password reset email containing instructions to reset their password. | Passed |  | Functional
TC# 007 | Logout Process | To verify whether the Logout Process Function working properly. | 1. Probashi App. 2. Internet Connection. | 1. Launch the "Probashi App.". 2. Navigate to the account dashboard. 3. Click on the "Logout" button. | Successful logout, terminating the user's session and redirecting to the login screen. | he logout process was successful. The user's session was terminated, and they were redirected to the login screen. | Passed |  | Functional